## 4
Published Shutdown Dated 04-July-2021
Date | SAP Notification | Scope Of Shutdown | Feeder Name | Feeder ID | Cluster | DTS/ PMT Name | DTS/ PMT ID | Availing Department | Time
2021-07-04 | 360126369 | INSTALLATION OF PMT AND LT LEADING CASE ID 404308305 | M.R. INDUSTRY | 3008 | Orangi | DTS-505734 : QADRI COMPOUND PMT : 400 KVA | 505734 | NC A50 R-1&2 | 10:00:00 - 18:00:00
2021-07-04 | 360126376 | RESHFITNIG OF HT POLE ,PMT AND SHIFTING OF SPAIN AND REINFORCEMENT OF PMT CASE ID 401424113 | MANGHOPIR ROAD | 868 | Orangi | DTS-007546 : P-92/16, GAFOOR MARBEL : 50 KVA | 7546 | NC A50 R-1&2 | 10:00:00 - 20:00:00
2021-07-04 | 360126379 | REINFORCEMENT OF PMT 150KVA TO 500KVA CASEID 404308322 | FAIZ-UR-REHMAN | 3149 | Orangi | DTS-512016 : P-12/1 SIMBA MECHANICAL PMT : 150 KVA | 512016 | NC A50 R-1&2 | 10:00:00 - 18:00:00
2021-07-04 | 360126678 | PMT INSTALLATION | CIVIL HOSPITAL-3 | 246 | Society | EXTRA AFFECTED: |  | PM Society Cluster | 09:00:00 - 18:30:00
2021-07-04 | 360126678 | PMT INSTALLATION | CIVIL HOSPITAL-3 | 246 | Society | BS-511219 : CIVIL HOSPITAL-3 BS BH1032 : KVA | BS-511219 | PM Society Cluster | 09:00:00 - 18:30:00
2021-07-04 | 360126678 | PMT INSTALLATION | CIVIL HOSPITAL-3 | 246 | Society | MRI CT SCAN PMT, CIVIL OPN THEATRE PMT REQUIRED DEAD IN ALL ASPECTS |  | PM Society Cluster | 09:00:00 - 18:30:00
2021-07-04 | 360126689 | S/S MESHING + EFI BOX INSTALLATION AT GRAMO PHONE FEEDER | GRAMO PHONE | 3109 | Orangi | DTS-523336 : M. ISMAIL BHATTI PMT : 100 KVA | 523336 | PM Orangi Cluster | 12:00:00 - 14:00:00
2021-07-04 | 360126689 | S/S MESHING + EFI BOX INSTALLATION AT GRAMO PHONE FEEDER | GRAMO PHONE | 3109 | Orangi | RM-02388 : GRAMOPHONE S/S : KVA | RM-02388 | PM Orangi Cluster | 12:00:00 - 14:00:00
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505738 : SALTEX F-718 PMT : 250 KVA | 505738 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126919 | PIBT S/S--G/MAINTENANCE TO BE REQUIRED | PIBT | 3463 | Bin Qasim | FDR-003463 : PIBT : 300 KVA |  | SSM Bin Qasim Clus | 10:22:20 - 17:23:52
2021-07-04 | 360126415 | PULLING OF SPAN CASE ID 105754972 | MURSHID HOSPITAL | 133 | Baldia | DTS-525107 : P-44/1 M. IKRAM KHAN : 150 KVA | 525107 | NC A50 R-1&2 | 10:00:00 - 18:00:00
2021-07-04 | 360126416 | PULLING OF SPAN CASE ID 105758878 | MEGATRON | 601 | Baldia | DTS-533251 : SAJID ALI : 250 KVA | 533251 | NC A50 R-1&2 | 10:00:00 - 18:00:00
2021-07-04 | 360126433 | ANTITHEFT DOOR INSTALLATION - REVENUE OFFICE | REVENUE OFFICE | 242 | Society | LOCAL AND LT PANEL REQUIRED DEAD IN ALL ASPECTS |  | SSM Cluster Societ | 08:30:00 - 18:30:00
2021-07-04 | 360126433 | ANTITHEFT DOOR INSTALLATION - REVENUE OFFICE | REVENUE OFFICE | 242 | Society | DTS-002056 : REVENUE OFFICE SS : 1000 KVA | 2056 | SSM Cluster Societ | 08:30:00 - 18:30:00
2021-07-04 | 360126434 | EFI INSTALLATION AT O/H CABLE POLE FAYYAZ TEX-2 SIDE | MALIR POULTRY FARM | 2179 | Orangi | O/H CABLE POLE |  | PM Orangi Cluster | 10:00:00 - 12:00:00
2021-07-04 | 360126539 | HT REFORCEMENT WITH TIGER CONDUCTOR AT P-30/12/4 TO P-30/12 & P-30/13 TO P-30/9 & P-30/9* TO P-30/9/4 & P-30/9/1 TO P-30/9/14 ON BOTH SIDE GROUND & SHORT | CRYSTAL ICE | 3233 | Surjani | HT REFORCEMENT WITH TIGER CONDUCTOR AT P-30/12/4 TO P-30/12 & P-30/13 TO P-30/9 & P-30/9* TO P-30/9/4 & P-30/9/1 TO P-30/9/14 ON BOTH SIDE GROUND & SHORT |  | IBC North Karachi | 09:00:00 - 17:30:00
2021-07-04 | 360126539 | HT REFORCEMENT WITH TIGER CONDUCTOR AT P-30/12/4 TO P-30/12 & P-30/13 TO P-30/9 & P-30/9* TO P-30/9/4 & P-30/9/1 TO P-30/9/14 ON BOTH SIDE GROUND & SHORT | CRYSTAL ICE | 3233 | Surjani | MAY BE WHOLE FEEDER AFFECTED. |  | IBC North Karachi | 09:00:00 - 17:30:00
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505731 : PERVEZ PMT : 150 KVA | 505731 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505732 : MANSOOR BARI PMT : 150 KVA | 505732 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505733 : ZAFAR & COMPANY PMT : 400 KVA | 505733 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505734 : QADRI COMPOUND PMT : 400 KVA | 505734 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505735 : ARIF SILK PMT : 500 KVA | 505735 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505736 : SARAH TEXILE PMT : 250 KVA | 505736 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505737 : SARHAD PLASTIC PMT : 500 KVA | 505737 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505739 : RRP S/S LOCAL : 750 KVA | 505739 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505748 : ALI HASHIM PMT : 100 KVA | 505748 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-505749 : RJ TEXTILE PMT : 250 KVA | 505749 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-509118 : NAZIA TANVEER PMT : 400 KVA | 509118 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-522749 : REHMAN SALEEM PACKAGES PMT : 500 KVA | 522749 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126591 | LT EXTENSION WORK UNDER HT | M.R. INDUSTRY | 3008 | Orangi | DTS-525040 : SARHAD PLASTIC INDUSTRIES : 250 KVA | 525040 | PM Orangi Cluster | 10:00:00 - 16:00:10
2021-07-04 | 360126648 | ABC PULLING/ OMR /DISMANTLING | MILLAT PRESS | 1338 | Defence | DTS-527266 : FAWAD YOUSUF : 250 KVA | 527266 | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126648 | ABC PULLING/ OMR /DISMANTLING | MILLAT PRESS | 1338 | Defence | COMPLETE LT & HT SD ON MENTIONED ABOVE PMT |  | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126648 | ABC PULLING/ OMR /DISMANTLING | MILLAT PRESS | 1338 | Defence | DTS-173019 : MILLAT PRESS S/S : 750 KVA | 173019 | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126648 | ABC PULLING/ OMR /DISMANTLING | MILLAT PRESS | 1338 | Defence | DTS-173028 : SHAIKH IQBAL AHMED : 250 KVA | 173028 | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126648 | ABC PULLING/ OMR /DISMANTLING | MILLAT PRESS | 1338 | Defence | DTS-529744 : AL REHMAT TRADE CENTRE RMU D/PMT LHS : 500 KVA | 529744 | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126648 | ABC PULLING/ OMR /DISMANTLING | MILLAT PRESS | 1338 | Defence | DTS-529745 : AL REHMAT TRADE CENTRE RMU D/PMT RHS : 500 KVA | 529745 | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126656 | CONVERSION OF HAZARDOUS HT OH INTO HT UG, HANGING OF HT CABLE ON HT POLES | SOUTH FEDERAL-B | 214 | Gulshan | DTS-002617 : P-92/1 B.S.MEGNA : 250 KVA | 2617 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126655 | IN SHAFEEQ #2 SS, P-8A SIDE FAULTY ISOLATOR REPLACE WITH SWITCH, 11KV BUS-BAR REQUIRED DEAD | SHAFIQ-II | 3604 | Gulshan | 11KV BUS-BAR REQUIRED DEAD |  | Centralize Gulshan | 09:30:00 - 15:30:00
2021-07-04 | 360126655 | IN SHAFEEQ #2 SS, P-8A SIDE FAULTY ISOLATOR REPLACE WITH SWITCH, 11KV BUS-BAR REQUIRED DEAD | SHAFIQ-II | 3604 | Gulshan | DTS-001298 : SHAFIQ TEXTILE SS : 1000 KVA | 1298 | Centralize Gulshan | 09:30:00 - 15:30:00
2021-07-04 | 360126656 | CONVERSION OF HAZARDOUS HT OH INTO HT UG, HANGING OF HT CABLE ON HT POLES | SOUTH FEDERAL-B | 214 | Gulshan | DTS-002607 : P- 92/B GULTEX CNG : 200 KVA | 2607 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126656 | CONVERSION OF HAZARDOUS HT OH INTO HT UG, HANGING OF HT CABLE ON HT POLES | SOUTH FEDERAL-B | 214 | Gulshan | DTS-002612 : P- 85 AQEEL TOWELS : 50 KVA | 2612 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126656 | CONVERSION OF HAZARDOUS HT OH INTO HT UG, HANGING OF HT CABLE ON HT POLES | SOUTH FEDERAL-B | 214 | Gulshan | DTS-002614 : MEENA TEXTILE : 750 KVA | 2614 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126656 | CONVERSION OF HAZARDOUS HT OH INTO HT UG, HANGING OF HT CABLE ON HT POLES | SOUTH FEDERAL-B | 214 | Gulshan | DTS-500275 : P- 92A MULTIMEDIA : 250 KVA | 500275 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126660 | ABC PULLING/ OMR /DISMANTLING | COTTON EXCHANGE | 184 | Defence | DTS-004266 : HAJI ADAM S/S : 500 KVA | 4266 | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126656 | CONVERSION OF HAZARDOUS HT OH INTO HT UG, HANGING OF HT CABLE ON HT POLES | SOUTH FEDERAL-B | 214 | Gulshan | DTS-171222 : CDGK PUMPING PMT : 200 KVA | 171222 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126656 | CONVERSION OF HAZARDOUS HT OH INTO HT UG, HANGING OF HT CABLE ON HT POLES | SOUTH FEDERAL-B | 214 | Gulshan | DTS-500345 : P- 84 RHS GHAZAL INDUSTRIES : 50 KVA | 500345 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126660 | ABC PULLING/ OMR /DISMANTLING | COTTON EXCHANGE | 184 | Defence | COMPLETE LT & HT SD ON MENTIONED ABOVE PMT FOR THE SAFE ISOLATION OF MILLAT PRESS FEEDER |  | E&C Protection | 10:00:00 - 17:00:00
2021-07-04 | 360126691 | RESAGGING OF HT O/H + EARTH WIRE AT NAURAS FEEDER | NAURAS | 3137 | Orangi | DTS-505497 : KWSB SITE PMT : 100 KVA | 505497 | PM Orangi Cluster | 12:00:00 - 14:00:00
2021-07-04 | 360126691 | RESAGGING OF HT O/H + EARTH WIRE AT NAURAS FEEDER | NAURAS | 3137 | Orangi | DTS-524371 : FEROZ TEXTILE IND. PMT : 100 KVA | 524371 | PM Orangi Cluster | 12:00:00 - 14:00:00
2021-07-04 | 360126691 | RESAGGING OF HT O/H + EARTH WIRE AT NAURAS FEEDER | NAURAS | 3137 | Orangi | DTS-531025 : JS STEEL MILLS PMT : 500 KVA | 531025 | PM Orangi Cluster | 12:00:00 - 14:00:00
2021-07-04 | 360126702 | SHUTDOWN REQUIRED DARUL FALAH S/S FOR CABLE SHIFTING FROM S/S TO NEW RMU ALL SIDES REQUIRED DEAD. | DARUL FALAH | 3694 | Korangi | SHUTDOWN REQUIRED DARUL FALAH S/S FOR CABLE SHIFTING FROM S/S TO NEW RMU ALL SIDES REQUIRED DEAD. |  | UGM Korangi Cluste | 09:00:00 - 16:00:00
2021-07-04 | 360126702 | SHUTDOWN REQUIRED DARUL FALAH S/S FOR CABLE SHIFTING FROM S/S TO NEW RMU ALL SIDES REQUIRED DEAD. | DARUL FALAH | 3694 | Korangi | FDR-003694 : DARUL FALAH : 300 KVA |  | UGM Korangi Cluste | 09:00:00 - 16:00:00
2021-07-04 | 360126702 | SHUTDOWN REQUIRED DARUL FALAH S/S FOR CABLE SHIFTING FROM S/S TO NEW RMU ALL SIDES REQUIRED DEAD. | DARUL FALAH | 3694 | Korangi | RM-01851 : DAR UL FALAH S/S : KVA | RM-01851 | UGM Korangi Cluste | 09:00:00 - 16:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-506064 : ANWAR SAEED PMT : 400 KVA | 506064 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-172548 : K.T.D.M.C. PMT : 500 KVA | 172548 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-172555 : INDUSTRIAL PARK PMT : 50 KVA | 172555 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-505973 : JAYSON FOOD PMT : 50 KVA | 505973 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-508140 : SHAMSA AHMED PMT : 250 KVA | 508140 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-508359 : M.IDREES PMT : 50 KVA | 508359 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-523188 : ASIF AYUB PMT : 250 KVA | 523188 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-528645 : MUHAMMAD IBRAHIM PMT : 250 KVA | 528645 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-530018 : RAJA SABRI KHAN PMT : 50 KVA | 530018 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-530743 : MUNEER AHMED SIDDIQUI : 100 KVA | 530743 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-530941 : MUHAMMAD MEHTAB : 500 KVA | 530941 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-532414 : DEEWAN MUHAMMAD YOUSUF FAROOQI : 50 KVA | 532414 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-532448 : JUBILEE CORPORATION : 100 KVA | 532448 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-532998 : AZIZ UL HAQ PMT : 100 KVA | 532998 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126711 | PMT QC WORK AND O/H JUMPERING | SILICON PRODUCT (OLD BURSHANE GAS) | 709 | Korangi | DTS-533143 : MIAN MUHAMMAD ALI PMT : 250 KVA | 533143 | PM Korangi Cluster | 09:00:00 - 17:00:00
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | DTS-008370 : SUKHIA GOTH-1 P13/2 (BOTA) : 250 KVA | 8370 | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | **COMPLETE FEEFER OFF REQUIRED** |  | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | DTS-008367 : AYUB GOTH-2 P14/4/MEDAN WLI : 250 KVA | 8367 | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | DTS-008368 : AYUB GOTH-1 P14/2/SIDIQUE BUT : 500 KVA | 8368 | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | DTS-173590 : P-13 AYUB GOTH/SULTAN TANKR : 250 KVA | 173590 | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | DTS-509016 : M/S LAL MUHAMMAD P-10/1 : 50 KVA | 509016 | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | DTS-523748 : JAMIA MASJID KHADIJA TUL QUBRA : 100 KVA | 523748 | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126720 | OH HT/LT SD REQUIRED FOR HT/LT POLES INSTALLATION + ABC PULLING + OMR UNDER COMPOSITE LINE | SAIFAL GOTH | 1282 | Johar | DTS-528576 : M/S CM PAK ZONG : 25 KVA | 528576 | E&C Protection | 09:00:47 - 18:01:48
2021-07-04 | 360126765 | MEENA TEXTILE SS ,ISOLATOR REPLACEMENT WITH OCB SWITCH 11 KV BUS-BAR REQUIRED DEAD IN S/S | SOUTH FEDERAL-B | 214 | Gulshan | 11 KV BUS-BAR ARE REQUIRED DEAD |  | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126765 | MEENA TEXTILE SS ,ISOLATOR REPLACEMENT WITH OCB SWITCH 11 KV BUS-BAR REQUIRED DEAD IN S/S | SOUTH FEDERAL-B | 214 | Gulshan | DTS-002614 : MEENA TEXTILE : 750 KVA | 2614 | Centralize Gulshan | 10:00:00 - 16:00:00
2021-07-04 | 360126793 | POLE COLIRING AND PMT LEADING CASE ID 104308218 | ALAMGIR | 828 | Orangi | DTS-531554 : AURUM CHEMICALS PMT : 100 KVA | 531554 | NC A50 R-1&2 | 10:00:00 - 18:00:00
2021-07-04 | 360126797 | CABLE TO BE OPENED & T-JOINT TO BE MADE OUT SIDE OF AL-HAAJ FAW MOTOR S/S | P.S.O II | 726 | Bin Qasim | BS-505942 : TAJ MOHAMMAD B/S (BH-1070) : KVA | BS-505942 | UGM Bin Qasim Clus | 12:00:00 - 18:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-008970 : BURHANI METAL PMT : 400 KVA | 8970 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-008971 : FAKHRI HERBAL PMT : 100 KVA | 8971 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-008972 : BURHANI TUBE PMT : 400 KVA | 8972 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-508097 : AURANGZAIB KHAN PMT : 150 KVA | 508097 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-512122 : ASSOCIATE WEAVERS PMT : 200 KVA | 512122 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-523954 : ABDUL WAHID PMT : 150 KVA | 523954 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-524474 : CHEMEX CORPORATION PMT : 500 KVA | 524474 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-526845 : GRACE INDUSTRIES PMT : 250 KVA | 526845 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-523986 : OMAN TEXTILE : 250 KVA | 523986 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126783 | SANA ULLAH SS, ISOLATOR REPLACEMENT WITH OCB SWITCH, 11 KV BUS-BAR ARE REQUIRED DEAD, | WONDER BREAD(LAL SHAHBAZ) | 1196 | Gulshan | 11KV BUS-BAR REQUIRED DEAD IN SS |  | Centralize Gulshan | 12:00:00 - 18:00:00
2021-07-04 | 360126783 | SANA ULLAH SS, ISOLATOR REPLACEMENT WITH OCB SWITCH, 11 KV BUS-BAR ARE REQUIRED DEAD, | WONDER BREAD(LAL SHAHBAZ) | 1196 | Gulshan | DTS-004800 : SANAULLAH : 750 KVA | 4800 | Centralize Gulshan | 12:00:00 - 18:00:00
2021-07-04 | 360126797 | CABLE TO BE OPENED & T-JOINT TO BE MADE OUT SIDE OF AL-HAAJ FAW MOTOR S/S | P.S.O II | 726 | Bin Qasim | DTS-522555 : SHAKIR HUSSAIN JIVANI PMT : 500 KVA | 522555 | UGM Bin Qasim Clus | 12:00:00 - 18:00:00
2021-07-04 | 360126797 | CABLE TO BE OPENED & T-JOINT TO BE MADE OUT SIDE OF AL-HAAJ FAW MOTOR S/S | P.S.O II | 726 | Bin Qasim | DTS-529759 : MUHAMMAD USMAN JHOKIO : 250 KVA | 529759 | UGM Bin Qasim Clus | 12:00:00 - 18:00:00
2021-07-04 | 360126823 | TREE PRUNING AT SOME POINTS OF MS CATTS FEEDER | MS CATTS | 1349 | Orangi | DTS-511311 : GULF TRADING PMT : 500 KVA | 511311 | IBC SITE | 10:06:12 - 13:00:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-503450 : BANK AL-FALAH PMT : 250 KVA | 503450 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-509667 : MUHAMMAD ISMAIL YOUSUF PMT : 150 KVA | 509667 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-524773 : ALI IQBAL PMT : 400 KVA | 524773 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-527301 : M. SOHAIL PMT : 50 KVA | 527301 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-527503 : ARCO ORGANICS PMT : 100 KVA | 527503 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-530390 : FAROOQ SITARA INTERNATIONAL PMT : 500 KVA | 530390 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-531157 : MS SEEMA PMT : 250 KVA | 531157 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126824 | TREE PRUNING AT SOME POINTS OF MUHAMMADI ROLLING FEEDER | MUHAMMADI ROLLING | 777 | Orangi | DTS-533498 : MISS SUMBUL PMT : 250 KVA | 533498 | IBC SITE | 11:00:00 - 12:30:00
2021-07-04 | 360126835 | EFI INSTALLATION OF SOME POINTS AT LYARI GEN. HOSPITAL S/S NIGHT SLUM FEEDER | NIGHT SLUM | 3285 | Baldia | RM-02384 : LYARI GEN. HOSPITAL S/S : KVA | RM-02384 | PM Baldia Cluster | 09:15:00 - 17:15:00
2021-07-04 | 360126851 | CHANGING DIRECTION OF LBS (P-36 OF MEGATRON FEEDER | MEGATRON | 601 | Baldia | POLE-36 (LBS POLE) |  | PM Baldia Cluster | 09:15:00 - 17:15:00
2021-07-04 | 360126906 | GENERAL MAINTENANCE & B/BAR SLEEVING WORK AT DALDA FOOD S/S | DALDA FOODS | 3545 | Bin Qasim | BS-527600 : DALDA FOODS B/S (BH-1376) : KVA | BS-527600 | UGM Bin Qasim Clus | 12:00:00 - 18:00:00
2021-07-04 | 360126836 | EARTHING WORK TO BE DONE...! | RP CONFECTIONARY | 188 | Surjani | FDR-000188 : RP CONFECTIONARY : 300 KVA |  | Centralize North C | 10:00:00 - 18:00:00
2021-07-04 | 360126836 | EARTHING WORK TO BE DONE...! | RP CONFECTIONARY | 188 | Surjani | EARTHING WORK TO BE DONE...! |  | Centralize North C | 10:00:00 - 18:00:00
Planned Shutdowns for Sunday the 4th July, 2021 Form No:- LDC-M-SD-W2/04
Date | Sr. No | Circuit / Equipment | Requesting Department | Purpose | Timing |  | Grid / Area Affected | Remarks
[5 empty] | From | To
2021-07-04 | 1 | 132kV Queensroad / Gizri circuit | GSMO-South TMS-OH | 1) For replacement of 132kV LA's of all three phases at Gizri grid (GSMO) 2) For maintenance & cleaning of line insulators (TMS) | 10:00 | 20:00 | Nil | 132kV Gizri / Clifton circuit will serve the load Work Permit No : PTW-040721-01-1 (For TMS-OH) Note: 132kV Ring will remain closed at Gizri
2021-07-04 | 2 | 132kV Landhi / Port Qasim circuit | TMS-OH Telecom | 1) For maintenance, cleaning of line insulators & attend hotspot red phase clamp at Landhi grid (TMS) 2) Maintenance of Telecom outdoor equipment at both ends (Telecom) | 10:00 | 17:00 | Nil | 132kV Pipri West / Landhi & Pipri West / KEPZ circuits will serve the load Work Permit No : PTW-040721-02-1 (For TMS-OH) Work Permit No : PTW-040721-02-2 (For Telecom)
2021-07-04 | 3 | 132kV Old Golimar / Mauripur circuit | TP-1000 TMS-UG | 1) For repairing DTS Fault (TP-1000) 2) Cleaning of 132kV cable sealing ends (TMS) | 07:30 | 12:30 | Nil | 132kV Old Golimar / Haroonabad circuit will serve the load Work Permit No : PTW-040721-03-1 (For TP-1000) Work Permit No : PTW-040721-03-2 (For TMS-UG)
2021-07-04 | 4 | 132kV Old Golimar / Haroonabad circuit |  |  | 13:00 | 18:00 |  | 132kV Old Golimar / Mauripur circuit will serve the load Work Permit No : PTW-040721-04-1 (For TP-1000) Work Permit No : PTW-040721-04-2 (For TMS-UG)
2021-07-04 | 5 | 132kV KDA / SNPC circuit 1 | STDC | Cleaning of insulators | 09:00 | 17:00 | Nil | 132kV KDA / SNPC circuit 2 will serve the load
2021-07-04 | 6 | Mauripur Grid, 31.5 / 40 MVA Trafo 2 | GSMO-North TMS-UG | 1) To replace DC Trip Unit at PTR 02 (GSMO) 2) For cleaning of 132kV cable sealing ends (TMS) | 10:00 | 14:00 | Nil | HT-Operation is informed for interruption RRC is informed for publishing Load will be served thru adjacent Trafo 1
2021-07-04 | 7 | K.West Grid, 31.5 / 40 MVA Trafo 1 | GSMO-Central Civil works | For safety Civil Rehabilitation work in 11 kV yard | 09:00 | 18:00 | Supply of K.E Korangi complex | HT-Operation is informed for load management & agreed to backfeed all feeders except K.E korangi complex supply feeder RRC is informed for publishing
|  |  | Feeder Name | Feeder ID
|  |  | BUNGASH-2 RMU | 3468
|  |  | FLEET MANAGEMENT | 3078
|  |  | FINE STAR | 3047
2021-07-04 | 8 | K.East Grid, 30 / 33 MVA Trafo 1 | GSMO-East | To install 11kV LA, replacement of 132kV supporting insulators, covering of 132 kV trench and installation of multifuncation meter | 10:00 | 18:00 | Nil | HT-Operation is informed for interruption RRC is informed for publishing Load will be served thru adjacent Trafo 2